Neil Shet

CIS 4374 Information Systems Project Management

Homework 1

Initial Kickoff (Version 1.0)

Vision and Scope

Project Acquisition

$oftware Corp. identified an opportunity to improve urban parking management through a digital platform that provides real-time parking information. The organization selected the Smart Parking Platform project because drivers waste significant time searching for parking spaces, while parking operators often lack efficient tools for monitoring occupancy and managing reservations. The project aims to improve the parking experience for users while increasing operational efficiency for parking facility operators.

Vision Statement

The Smart Parking Platform will provide drivers with a convenient method to locate, reserve, and pay for parking spaces through a web and mobile application. The platform will reduce time spent searching for parking and improve parking facility utilization.

Project Scope

The project includes:

- User account registration and login

- Parking space search

- Real-time parking availability

- Parking reservations

- Digital payment processing

- Navigation assistance

- Notifications and alerts

- Administrative dashboard

- Occupancy reporting and analytics

The project excludes:

- Physical parking garage construction

- Hardware installation within parking facilities

- Vehicle maintenance services

Competitive Analysis

ParkMobile

Strengths:

- Widely used

- Simple mobile payments

- Real-time parking sessions

Weaknesses:

- Limited reservation availability in some areas

- Depends on participating cities

ParkWhiz

Strengths:

- Event parking reservations

- User-friendly interface

Weaknesses:

- Less focus on real-time occupancy data

SpotHero

Strengths:

- Advanced reservations

- Large network of garages

- Price comparisons

Weaknesses:

- Availability varies by city

Opportunity for Differentiation

Our Smart Parking Platform will differentiate itself through:

- Real-time occupancy tracking

- AI-based parking recommendations

- Predictive availability forecasting

- Dynamic pricing suggestions

- Unified mobile and web experience

Stakeholders

| Stakeholder | Interest |
| --- | --- |
| Drivers | Find parking quickly |
| Parking Operators | Increase utilization |
| City Transportation Departments | Reduce congestion |
| System Administrators | System maintenance |
| Finance Personnel | Payment processing |
| Payment Providers | Payment integration |

Initial Use Cases

Use Case 1: Register Account

Actor: Driver

Goal: Create an account.

Basic Flow:

- User enters information.

- System validates information.

- Account is created.

Use Case 2: Search for Parking

Actor: Driver

Goal: Find available parking.

Basic Flow:

- User enters destination.

- System displays nearby garages.

- User views availability.

Use Case 3: Reserve Parking Spot

Actor: Driver

Goal: Reserve a parking spot.

Use Case 4: Make Payment

Actor: Driver

Goal: Pay for reservation.

Use Case 5: View Occupancy Dashboard

Actor: Parking Operator

Goal: Monitor garage utilization.

Initial Requirements

Functional Requirements

FR-1: The system shall allow user registration.

FR-2: The system shall display real-time parking availability.

FR-3: The system shall allow parking reservations.

FR-4: The system shall process online payments.

FR-5: The system shall generate occupancy reports.

Nonfunctional Requirements

NFR-1: System uptime must be 99%.

NFR-2: Payment transactions must be encrypted.

NFR-3: Mobile pages should load within 3 seconds.

NFR-4: Platform must support at least 10,000 users.

Homework 2

Deliverables (WBS/Draft Timeline) (Version 2.0)

Work Breakdown Structure (WBS)

1.0 Authentication System

1.1 User Registration

- 1.1.1 Registration Form

- 1.1.2 Account Validation

- 1.1.3 Account Creation

1.2 User Login

- 1.2.1 Login Screen

- 1.2.2 Credential Verification

- 1.2.3 Session Management

2.0 Parking Search and Reservation

2.1 Parking Search

- 2.1.1 Location Search

- 2.1.2 Map Display

- 2.1.3 Availability Display

2.2 Parking Reservation

- 2.2.1 Create Reservation

- 2.2.2 Modify Reservation

- 2.2.3 Cancel Reservation

3.0 Payment Processing

3.1 Payment Integration

- 3.1.1 Payment Gateway Setup

- 3.1.2 Secure Transaction Processing

- 3.1.3 Receipt Generation

3.2 Financial Records

- 3.2.1 Payment History

- 3.2.2 Billing Reports

4.0 Administrative Dashboard

4.1 Parking Operator Management

- 4.1.1 Garage Management

- 4.1.2 Space Availability Updates

- 4.1.3 User Management

4.2 Reporting and Analytics

- 4.2.1 Occupancy Reports

- 4.2.2 Revenue Reports

- 4.2.3 Usage Analytics

5.0 Notifications and Navigation

5.1 Notifications

- 5.1.1 Reservation Confirmation

- 5.1.2 Payment Confirmation

- 5.1.3 Parking Reminders

5.2 Navigation Services

- 5.2.1 Mapping Integration

- 5.2.2 Route Guidance

- 5.2.3 Destination Assistance

Project Schedule

| Task ID | Task | Duration |
| --- | --- | --- |
| 1 | Requirements Analysis | 1 Week |
| 2 | System Design | 1 Week |
| 3 | Authentication Development | 1 Week |
| 4 | Parking Search Development | 1 Week |
| 5 | Reservation System Development | 1 Week |
| 6 | Payment Integration | 1 Week |
| 7 | Administrative Dashboard | 1 Week |
| 8 | Notifications & Navigation | 1 Week |
| 9 | Testing & Quality Assurance | 1 Week |
| 10 | Final Project Review | 1 Week |

Dependencies

- System Design begins after Requirements Analysis.

- Authentication Development begins after System Design.

- Parking Search Development begins after Authentication Development.

- Reservation System Development begins after Parking Search Development.

- Payment Integration begins after Reservation System Development.

- Administrative Dashboard begins after Payment Integration.

- Notifications & Navigation begins after Administrative Dashboard.

- Testing & Quality Assurance begins after all development activities are complete.

- Final Project Review begins after Testing & Quality Assurance.

Gantt Chart (Draft)

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Analysis | X |  |  |  |  |  |  |  |  |  |
| System Design |  | X |  |  |  |  |  |  |  |  |
| Authentication Development |  |  | X |  |  |  |  |  |  |  |
| Parking Search Development |  |  |  | X |  |  |  |  |  |  |
| Reservation System Development |  |  |  |  | X |  |  |  |  |  |
| Payment Integration |  |  |  |  |  | X |  |  |  |  |
| Administrative Dashboard |  |  |  |  |  |  | X |  |  |  |
| Notifications & Navigation |  |  |  |  |  |  |  | X |  |  |
| Testing & QA |  |  |  |  |  |  |  |  | X |  |
| Final Review |  |  |  |  |  |  |  |  |  | X |

Project Milestones

Milestone 1: Requirements Approved (End of Week 1)

Milestone 2: System Design Completed (End of Week 2)

Milestone 3: Core User Features Completed (End of Week 5)

Milestone 4: Payment Processing Completed (End of Week 6)

Milestone 5: System Testing Completed (End of Week 9)

Milestone 6: Final Project Submission (End of Week 10)

Copilot Office 365 provided by UH was utilized as an analytical tool to assist in organizing data. All final analytical conclusions, evidence verification, source selection, and narrative text were critically reviewed, edited, and approved by the student author.

References

ParkMobile parking app: Find & Pay For Parking: On-Street & Reservation. ParkMobile.		 (n.d.). https://parkmobile.io/

Find and book parking anywhere. ParkWhiz. (n.d.). https://www.parkwhiz.com/

Get everywhere easier: Reserve parking and save. SpotHero. (n.d.). https://spothero.com/