Neil Shet

CIS 4374 Information Systems Project Management

Homework 1

Initial Kickoff (Version 1.0)

Vision and Scope

Project Acquisition

$oftware Corp. identified an opportunity to improve urban parking management through a digital platform that provides real-time parking information. The organization selected the Smart Parking Platform project because drivers waste significant time searching for parking spaces, while parking operators often lack efficient tools for monitoring occupancy and managing reservations. The project aims to improve the parking experience for users while increasing operational efficiency for parking facility operators.

Vision Statement

The Smart Parking Platform will provide drivers with a convenient method to locate, reserve, and pay for parking spaces through a web and mobile application. The platform will reduce time spent searching for parking and improve parking facility utilization.

Project Scope

The project includes:

- User account registration and login

- Parking space search

- Real-time parking availability

- Parking reservations

- Digital payment processing

- Navigation assistance

- Notifications and alerts

- Administrative dashboard

- Occupancy reporting and analytics

The project excludes:

- Physical parking garage construction

- Hardware installation within parking facilities

- Vehicle maintenance services

Competitive Analysis

ParkMobile

Strengths:

- Widely used

- Simple mobile payments

- Real-time parking sessions

Weaknesses:

- Limited reservation availability in some areas

- Depends on participating cities

ParkWhiz

Strengths:

- Event parking reservations

- User-friendly interface

Weaknesses:

- Less focus on real-time occupancy data

SpotHero

Strengths:

- Advanced reservations

- Large network of garages

- Price comparisons

Weaknesses:

- Availability varies by city

Opportunity for Differentiation

Our Smart Parking Platform will differentiate itself through:

- Real-time occupancy tracking

- AI-based parking recommendations

- Predictive availability forecasting

- Dynamic pricing suggestions

- Unified mobile and web experience

Stakeholders

| Stakeholder | Interest |
| --- | --- |
| Drivers | Find parking quickly |
| Parking Operators | Increase utilization |
| City Transportation Departments | Reduce congestion |
| System Administrators | System maintenance |
| Finance Personnel | Payment processing |
| Payment Providers | Payment integration |

Initial Use Cases

Use Case 1: Register Account

Actor: Driver

Goal: Create an account.

Basic Flow:

- User enters information.

- System validates information.

- Account is created.

Use Case 2: Search for Parking

Actor: Driver

Goal: Find available parking.

Basic Flow:

- User enters destination.

- System displays nearby garages.

- User views availability.

Use Case 3: Reserve Parking Spot

Actor: Driver

Goal: Reserve a parking spot.

Use Case 4: Make Payment

Actor: Driver

Goal: Pay for reservation.

Use Case 5: View Occupancy Dashboard

Actor: Parking Operator

Goal: Monitor garage utilization.

Initial Requirements

Functional Requirements

FR-1: The system shall allow user registration.

FR-2: The system shall display real-time parking availability.

FR-3: The system shall allow parking reservations.

FR-4: The system shall process online payments.

FR-5: The system shall generate occupancy reports.

Nonfunctional Requirements

NFR-1: System uptime must be 99%.

NFR-2: Payment transactions must be encrypted.

NFR-3: Mobile pages should load within 3 seconds.

NFR-4: Platform must support at least 10,000 users.

Homework 2

Deliverables (WBS/Draft Timeline) (Version 2.0)

Work Breakdown Structure (WBS)

1.0 Authentication System

1.1 User Registration

- 1.1.1 Registration Form

- 1.1.2 Account Validation

- 1.1.3 Account Creation

1.2 User Login

- 1.2.1 Login Screen

- 1.2.2 Credential Verification

- 1.2.3 Session Management

2.0 Parking Search and Reservation

2.1 Parking Search

- 2.1.1 Location Search

- 2.1.2 Map Display

- 2.1.3 Availability Display

2.2 Parking Reservation

- 2.2.1 Create Reservation

- 2.2.2 Modify Reservation

- 2.2.3 Cancel Reservation

3.0 Payment Processing

3.1 Payment Integration

- 3.1.1 Payment Gateway Setup

- 3.1.2 Secure Transaction Processing

- 3.1.3 Receipt Generation

3.2 Financial Records

- 3.2.1 Payment History

- 3.2.2 Billing Reports

4.0 Administrative Dashboard

4.1 Parking Operator Management

- 4.1.1 Garage Management

- 4.1.2 Space Availability Updates

- 4.1.3 User Management

4.2 Reporting and Analytics

- 4.2.1 Occupancy Reports

- 4.2.2 Revenue Reports

- 4.2.3 Usage Analytics

5.0 Notifications and Navigation

5.1 Notifications

- 5.1.1 Reservation Confirmation

- 5.1.2 Payment Confirmation

- 5.1.3 Parking Reminders

5.2 Navigation Services

- 5.2.1 Mapping Integration

- 5.2.2 Route Guidance

- 5.2.3 Destination Assistance

Project Schedule

| Task ID | Task | Duration |
| --- | --- | --- |
| 1 | Requirements Analysis | 1 Week |
| 2 | System Design | 1 Week |
| 3 | Authentication Development | 1 Week |
| 4 | Parking Search Development | 1 Week |
| 5 | Reservation System Development | 1 Week |
| 6 | Payment Integration | 1 Week |
| 7 | Administrative Dashboard | 1 Week |
| 8 | Notifications & Navigation | 1 Week |
| 9 | Testing & Quality Assurance | 1 Week |
| 10 | Final Project Review | 1 Week |

Dependencies

- System Design begins after Requirements Analysis.

- Authentication Development begins after System Design.

- Parking Search Development begins after Authentication Development.

- Reservation System Development begins after Parking Search Development.

- Payment Integration begins after Reservation System Development.

- Administrative Dashboard begins after Payment Integration.

- Notifications & Navigation begins after Administrative Dashboard.

- Testing & Quality Assurance begins after all development activities are complete.

- Final Project Review begins after Testing & Quality Assurance.

Gantt Chart (Draft)

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Analysis | X |  |  |  |  |  |  |  |  |  |
| System Design |  | X |  |  |  |  |  |  |  |  |
| Authentication Development |  |  | X |  |  |  |  |  |  |  |
| Parking Search Development |  |  |  | X |  |  |  |  |  |  |
| Reservation System Development |  |  |  |  | X |  |  |  |  |  |
| Payment Integration |  |  |  |  |  | X |  |  |  |  |
| Administrative Dashboard |  |  |  |  |  |  | X |  |  |  |
| Notifications & Navigation |  |  |  |  |  |  |  | X |  |  |
| Testing & QA |  |  |  |  |  |  |  |  | X |  |
| Final Review |  |  |  |  |  |  |  |  |  | X |

Project Milestones

Milestone 1: Requirements Approved (End of Week 1)

Milestone 2: System Design Completed (End of Week 2)

Milestone 3: Core User Features Completed (End of Week 5)

Milestone 4: Payment Processing Completed (End of Week 6)

Milestone 5: System Testing Completed (End of Week 9)

Milestone 6: Final Project Submission (End of Week 10)

Homework 3

Product Backlog using Trello (Version 3.0)

Sprint 1 Status Update

Homework 4

Risk Management and Communication Plan (Version 4.0)

Risk Identification

Technical Risks

- Payment gateway integration may fail or experience compatibility issues.

- Real-time parking availability data may be inaccurate or delayed.

- Security vulnerabilities could expose user information.

- System performance may degrade under high user traffic.

Schedule Risks

- Development tasks may take longer than estimated.

- Testing may identify major defects requiring rework.

- Requirement changes could delay project completion.

- Dependencies between project tasks may create bottlenecks.

Financial Risks

- Development costs may exceed the planned budget.

- Third-party service fees may increase unexpectedly.

- Additional software or licensing costs may be required.

- Payment processing expenses could be higher than anticipated.

People Risks

- Team members may become unavailable during the project.

- Communication breakdowns could delay progress.

- Stakeholder feedback may not be received on time.

- Team members may lack expertise in certain project areas.

| ID | Risk Description | Probability | Impact | Owner | Response Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Payment gateway integration failure | Medium | High | Development Team | Conduct early integration testing | Monitoring |
| R2 | Inaccurate parking availability data | Medium | High | Technical Lead | Implement data validation checks | Open |
| R3 | Security vulnerabilities | Medium | High | Security Team | Perform regular security testing | Open |
| R4 | System performance issues | Medium | Medium | Development Team | Conduct performance testing | Open |
| R5 | Schedule delays | Medium | High | Project Manager | Monitor milestones weekly | Monitoring |
| R6 | Requirement changes | Medium | Medium | Project Manager | Use change control procedures | Open |
| R7 | Budget overruns | Low | High | Finance Team | Review project budget regularly | Open |
| R8 | Increased third-party service costs | Low | Medium | Finance Team | Monitor vendor contracts | Open |
| R9 | Team member unavailability | Low | Medium | Project Manager | Cross-train team members | Open |
| R10 | Delayed stakeholder feedback | Medium | Medium | Project Manager | Schedule recurring review meetings | Monitoring |

Several project risks continue to be monitored. No high-priority risks have materialized at this stage of the project.

Communication Plan

Meeting Cadence

| Team/Stakeholder Group | Frequency | Communication Method | Purpose |
| --- | --- | --- | --- |
| Project Team | Weekly | Microsoft Teams | Project status updates |
| Development Team | Twice Weekly | Teams/Trello | Progress tracking and issue resolution |
| Testing Team | Weekly | Microsoft Teams | Testing and defect reviews |
| Stakeholders | Bi-Weekly | Teams/Email | Project updates and feedback |
| Finance Team | Monthly | Email/Meeting | Budget and cost review |

Communication Status Update

- Weekly project meetings are being conducted as scheduled.

- Sprint progress is tracked through Trello.

- Stakeholder communication remains on schedule.

Reporting Methods

- Weekly project status reports

- Trello board updates

- Sprint review meetings

- Email progress summaries

- Milestone completion reports

- Final project presentation

Homework 5

Roles & Resources, Resource & Cost Plan, and RACI Matrix (Version 5.0)

Roles & Resources

The Smart Parking Platform project requires a cross-functional team responsible for planning, designing, developing, testing, and managing the system.

| Role | Team Member | Skill Level | Allocation |
| --- | --- | --- | --- |
| Project Manager | Sarah Johnson | Senior | 20% |
| Business Analyst | Michael Lee | Intermediate | 15% |
| Developer 1 | Alex Carter | Senior | 40% |
| Developer 2 | Emily Davis | Intermediate | 40% |
| QA Tester | Daniel Brown | Intermediate | 20% |
| UI/UX Designer | Jessica Wilson | Intermediate | 15% |

Resource Assumptions

- The Project Manager oversees scheduling, risk management, and communication.

- The Business Analyst gathers and validates requirements.

- Developers are responsible for application development and integration.

- The QA Tester performs testing and quality assurance activities.

- The UI/UX Designer creates user-friendly interfaces for both drivers and parking operators.

Resource & Cost Plan

Bottom-Up Cost Estimate

| Role | Estimated Hours | Hourly Rate | Cost |
| --- | --- | --- | --- |
| Project Manager | 80 | $50 | $4,000 |
| Business Analyst | 60 | $40 | $2,400 |
| Developer 1 | 160 | $45 | $7,200 |
| Developer 2 | 160 | $45 | $7,200 |
| QA Tester | 80 | $35 | $2,800 |
| UI/UX Designer | 40 | $40 | $1,600 |

- Labor Cost Total: $25,200

### Resource Utilization Update

- The project team continues to operate within the planned resource allocations. No additional staffing or budget adjustments are required at this time.

- This is a very normal project update.

Additional Project Expenses

| Expense Item | Cost |
| --- | --- |
| Cloud Hosting Services | $600 |
| Software Licenses | $500 |
| Third-Party API Integration | $400 |
| Contingency Reserve (10%) | $2,670 |

- Total Estimated Project Cost: $29,370

Budgeted Monthly Cash Flow

| Month | Labor Cost | Infrastructure | Tools/APIs | Total Cost |
| --- | --- | --- | --- | --- |
| Month 1 | $8,400 | $200 | $250 | $8,850 |
| Month 2 | $8,400 | $200 | $250 | $8,850 |
| Month 3 | $8,400 | $200 | $400 | $9,000 |

- Total Budget: $26,700

RACI Matrix

R = Responsible

A = Accountable

C = Consulted

I = Informed

| Project Activity | PM | BA | DEV | QA | UI/UX |
| --- | --- | --- | --- | --- | --- |
| Requirements Gathering | A | R | I | I | C |
| System Design | A | C | R | I | C |
| User Interface Design | I | C | C | I | R/A |
| Authentication Development | C | I | R/A | I | I |
| Parking Search Development | C | I | R/A | I | C |
| Reservation System Development | C | I | R/A | I | I |
| Payment Integration | C | I | R/A | I | I |
| Dashboard Development | C | I | R/A | I | C |
| Testing & Quality Assurance | I | I | C | R/A | I |
| Deployment | A | I | R | C | I |
| Final Project Review | A | C | C | C | I |

Copilot Office 365 provided by UH was utilized as an analytical tool to assist in organizing data. All final analytical conclusions, evidence verification, source selection, and narrative text were critically reviewed, edited, and approved by the student author.

References

ParkMobile parking app: Find & Pay For Parking: On-Street & Reservation. ParkMobile.		 (n.d.). https://parkmobile.io/

Find and book parking anywhere. ParkWhiz. (n.d.). https://www.parkwhiz.com/

Get everywhere easier: Reserve parking and save. SpotHero. (n.d.). https://spothero.com/